## EXAMPLE_project-drawdown-schedu
Description of Work | Original Budget | Pre-construction Costs | Draw Request 1 | Draw Request 2 | Draw Request 3 | Draw Request 4 | Draw Request 5 | Draw Request 6 | Draw Request 7 | Draw Request 8 | Draw Request 9 | Draw Request 10 | Contingency | Remaining (Use to Check Math)
|  |  | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01
Soft Costs
- Land Acquisition | 10000 | 10000 | [11 empty] | 0
- Environmental Review Notice and ESA I | 10000 | 10000 | [11 empty] | 0
- Office Utilities During Pre-development | 10000 | 10000 | [11 empty] | 0
- Value Engineering | 10000 | 10000 | [11 empty] | 0
- Permits & Fees | 10000 | 10000 | [11 empty] | 0
- Appraisal | 10000 | 10000 | [11 empty] | 0
- Property Tax | 10000 | 10000 | [11 empty] | 0
- Operating Reserves | 10000 | 10000 | [11 empty] | 0
- Office Supplies | 10000 |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 0
- Bookkeeping | 10000 |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 0
- Housing Market Study | 10000 | 10000 | [11 empty] | 0
- Marketing | 10000 |  | 2025-07-01: 2500; 2025-08-01: 2500; 2025-09-01: 2500; 2025-10-01: 2500 |  | 0
- Contract Documents | 10000 | 10000 | [11 empty] | 0
- Title Report | 10000 | 10000 | [11 empty] | 0
- Construction Loan Recording Fee | 10000 | 10000 | [11 empty] | 0
- Soft Cost Contingency | 10000 | [11 empty] | 10000 | 0
- Developer's Fee (non-deferred) | 10000 | 10000 | [11 empty] | 0
- Permanent Loan Fees | 10000 | 10000 | [11 empty] | 0
- Monthly Construction Inspections | 10000 |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 0
- Contractor's Overhead | 10000 |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 0
- Contractor's Travel and Lodging | 10000 |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 0
- Contractor's Profit | 10000 |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 0
- General Requirements | 10000 |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 0
Building Construction
- Excavation, Footer, Stemwall | 10000 |  | 2025-02-01: 2500; 2025-03-01: 2500; 2025-04-01: 2500; 2025-05-01: 2500 |  | 0
- French Drain, Moisture, and Waterproofing Foundation | 10000 |  | 2025-06-01: 5000; 2025-07-01: 5000 |  | 0
- Rough Framing | 10000 |  | 2025-02-01: 2500; 2025-03-01: 2500; 2025-04-01: 2500; 2025-05-01: 2500 |  | 0
- Rough Plumbing | 10000 |  | 2025-03-01: 2500; 2025-04-01: 2500; 2025-05-01: 2500; 2025-06-01: 2500 |  | 0
- Rough Electric | 10000 |  | 2025-04-01: 5000; 2025-05-01: 5000 |  | 0
- Rough HVAC | 10000 |  | 2025-04-01: 5000; 2025-05-01: 5000 |  | 0
- Roofing | 10000 |  | 2025-04-01: 5000; 2025-05-01: 2500; 2025-06-01: 2500 |  | 0
- Insulation and Drywall | 10000 |  | 2025-05-01: 5000; 2025-06-01: 2500; 2025-07-01: 2500 |  | 0
- Windows and Exterior Doors | 10000 |  | 2025-04-01: 5000; 2025-05-01: 2500; 2025-06-01: 2500 |  | 0
- Exterior Siding, Fascia, Soffits, and Gutter/Downspout | 10000 |  | 2025-04-01: 2000; 2025-05-01: 2000; 2025-06-01: 2000; 2025-07-01: 2000; 2025-08-01: 2000 |  | 0
- Interior Doors and Trim | 10000 |  | 2025-06-01: 5000; 2025-07-01: 5000 |  | 0
- Interior Paint | 10000 |  | 2025-05-01: 2500; 2025-06-01: 5000; 2025-07-01: 2500 |  | 0
- Flooring | 10000 |  | 2025-07-01: 5000; 2025-08-01: 5000 |  | 0
- Finish Electric | 10000 |  | 2025-07-01: 5000; 2025-08-01: 5000 |  | 0
- Finish Plumbing | 10000 |  | 2025-07-01: 5000; 2025-08-01: 5000 |  | 0
- Cabinet and Countertops | 10000 |  | 2025-08-01: 5000; 2025-09-01: 5000 |  | 0
- Finish HVAC | 10000 |  | 2025-08-01: 5000; 2025-09-01: 5000 |  | 0
- Exterior Concrete | 10000 |  | 2025-09-01: 5000; 2025-10-01: 5000 |  | 0
- Punch List | 10000 |  | 2025-10-01: 10000 |  | 0
Construction Contingency | 10000 | [11 empty] | 10000 | 0
Construction Loan Fees | 10000 | 10000 | [11 empty] | 0
Interest Reserves | 10000 | 10000
Retainage Held (5%) |  |  | -200 | -450 | -575 | -1675 | -1800 | -1550 | -1800 | -1550 | -950 | 10550 |  | 0
TOTAL USES | 450000 | 160000 | 6800 | 11550 | 13925 | 34825 | 37200 | 32450 | 39700 | 34950 | 23550 | 35050 | 20000 | 0
% Complete |  | 35.56% | 37.07% | 39.63% | 42.73% | 50.47% | 58.73% | 65.94% | 74.77% | 82.53% | 87.77% | 95.56% | 100%
% of Total |  | 35.56% | 1.511% | 2.567% | 3.094% | 7.739% | 8.267% | 7.211% | 8.822% | 7.767% | 5.233% | 7.789% | 4.444%
Sources
Donations | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Complete of Donations |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
% of Total of Donations |  | 100% | [10 empty] | 0% | bar: 2025-01-01 to 2025-10-01
Pre-development Grant | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Complete of Pre-development Grant |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
% of Total of Pre-development Grant |  | 100% | [10 empty] | 0% | bar: 2025-01-01 to 2025-10-01
Construction Grant | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Complete of Construction Grant |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
% of Total of Construction Grant |  | 100% | [10 empty] | 0% | bar: 2025-01-01 to 2025-10-01
Construction Loan | 340000 | 50000 | 6800 | 11550 | 13925 | 34825 | 37200 | 32450 | 39700 | 34950 | 23550 | 35050 | 20000 | 0
% Complete of Construction Loan |  | 14.71% | 16.71% | 20.1% | 24.2% | 34.44% | 45.38% | 54.93% | 66.6% | 76.88% | 83.81% | 94.12% | 100%
% of Total of Construction Loan |  | 14.71% | 2% | 3.397% | 4.096% | 10.24% | 10.94% | 9.544% | 11.68% | 10.28% | 6.926% | 10.31% | 5.882%
TOTAL SOURCES EXPENDED | 450000 | 160000 | 6800 | 11550 | 13925 | 34825 | 37200 | 32450 | 39700 | 34950 | 23550 | 35050 | 20000 | 0
% Complete |  | 35.56% | 37.07% | 39.63% | 42.73% | 50.47% | 58.73% | 65.94% | 74.77% | 82.53% | 87.77% | 95.56% | 100%
% of Total |  | 35.56% | 1.511% | 2.567% | 3.094% | 7.739% | 8.267% | 7.211% | 8.822% | 7.767% | 5.233% | 7.789% | 4.444%
SOURCES MINUS USES (Use to Check Math) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BLANK_project-drawdown-schedule
Description of Work | Original Budget | Pre-construction Costs | Draw Request 1 | Draw Request 2 | Draw Request 3 | Draw Request 4 | Draw Request 5 | Draw Request 6 | Draw Request 7 | Draw Request 8 | Draw Request 9 | Draw Request 10 | Contingency | Remaining (Use to Check Math)
|  |  | YEAR MONTH | YEAR MONTH | YEAR MONTH | YEAR MONTH | YEAR MONTH | YEAR MONTH | YEAR MONTH | YEAR MONTH | YEAR MONTH | YEAR MONTH
Soft Costs
- Land Acquisition | [13 empty] | 0
- Environmental Review Notice and ESA I | [13 empty] | 0
- Office Utilities During Pre-development | [13 empty] | 0
- Value Engineering | [13 empty] | 0
- Permits & Fees | [13 empty] | 0
- Appraisal | [13 empty] | 0
- Property Tax | [13 empty] | 0
- Operating Reserves | [13 empty] | 0
- Office Supplies | [13 empty] | 0
- Bookkeeping | [13 empty] | 0
- Housing Market Study | [13 empty] | 0
- Marketing | [13 empty] | 0
- Contract Documents | [13 empty] | 0
- Title Report | [13 empty] | 0
- Construction Loan Recording Fee | [13 empty] | 0
- Soft Cost Contingency | [13 empty] | 0
- Developer's Fee (non-deferred) | [13 empty] | 0
- Permanent Loan Fees | [13 empty] | 0
- Monthly Construction Inspections | [13 empty] | 0
- Contractor's Overhead | [13 empty] | 0
- Contractor's Travel and Lodging | [13 empty] | 0
- Contractor's Profit | [13 empty] | 0
- General Requirements | [13 empty] | 0
Building Construction
- Excavation, Footer, Stemwall | [13 empty] | 0
- French Drain, Moisture, and Waterproofing Foundation | [13 empty] | 0
- Rough Framing | [13 empty] | 0
- Rough Plumbing | [13 empty] | 0
- Rough Electric | [13 empty] | 0
- Rough HVAC | [13 empty] | 0
- Roofing | [13 empty] | 0
- Insulation and Drywall | [13 empty] | 0
- Windows and Exterior Doors | [13 empty] | 0
- Exterior Siding, Fascia, Soffits, and Gutter/Downspout | [13 empty] | 0
- Interior Doors and Trim | [13 empty] | 0
- Interior Paint | [13 empty] | 0
- Flooring | [13 empty] | 0
- Finish Electric | [13 empty] | 0
- Finish Plumbing | [13 empty] | 0
- Cabinet and Countertops | [13 empty] | 0
- Finish HVAC | [13 empty] | 0
- Exterior Concrete | [13 empty] | 0
- Punch List | [13 empty] | 0
Construction Contingency | [13 empty] | 0
Developer Contingency | [13 empty] | 0
Construction Loan Fees | [13 empty] | 0
Interest Reserves | [13 empty] | 0
Retainage Held (5%) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
TOTAL USES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Complete |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% of Total |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Sources
Donations | [13 empty] | 0
% Complete of Donations |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% of Total of Donations |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Pre-development Grant | [13 empty] | 0
% Complete of Pre-development Grant |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% of Total of Pre-development Grant |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Construction Grant | [13 empty] | 0
% Complete of Construction Grant |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% of Total of Construction Grant |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Construction Loan | [13 empty] | 0
% Complete of Construction Loan |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% of Total of Construction Loan |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TOTAL SOURCES EXPENDED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Complete |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% of Total |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
SOURCES MINUS USES (Use to Check Math) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0